## 1_Summary_Scoring
ERP Readiness Checklist — Summary & Scoring
Prepared: [DATE] | Max Score | Your Score | Notes
Business Outcomes & Scope | 20 | 7
Process Mapping | 20 | 2
Data & Integration | 20 | 1
People & Change | 20 | 2
Security & Compliance | 10 | 1
Vendor Shortlist & Evaluation | 20 | 0
Pilot & Rollout Plan | 20 | 0
Budget & TCO | 10 | 0
TOTAL | 130 | 13
How to use:
1) Complete each section's Status and Score (0=No, 1=Partial, 2=Ready).
2) Summarise scores here to track readiness over time.
3) Anything 'Not Started' with High risk needs an owner and due date.

## 2_Business_Outcomes_Scope
Priority (H/M/L) | Requirement / Question | Evidence / Notes | Owner | Status | Due Date | Risk (L/M/H) | Mitigation | Score (0-2)
H | We have 3–5 measurable outcomes (e.g., reduce stockouts 30%, 5-day faster close). |  |  | Not started |  | H |  | 1
H | We have a clear initial scope (Phase 1 foundations; later phases documented). |  |  |  |  | M |  | 2
M | Success metrics and baselines defined for each outcome. | [6 empty] | 1
M | Executive sponsor and steering cadence agreed. | [6 empty] | 1
L | Benefits realisation plan drafted (90-day value sprints). | [6 empty] | 2
7

## 3_Process_Mapping
Priority (H/M/L) | Requirement / Question | Evidence / Notes | Owner | Status | Due Date | Risk (L/M/H) | Mitigation | Score (0-2)
H | Order-to-Cash mapped (quotes, pricing, fulfilment, invoicing, returns). |  |  | In progress |  | H |  | 2
H | Procure-to-Pay mapped (requisitions, approvals, receipts, AP).
H | Record-to-Report mapped (period close, journals, consolidation).
M | Plan-to-Produce / Jobs-to-Cash mapped (if manufacturing/projects).
M | Warehouse flows mapped (FEFO/serials/bins/3PL/site deliveries).
L | Exception workflows and controls documented.
2

## 4_Data_Integration
Priority (H/M/L) | Requirement / Question | Evidence / Notes | Owner | Status | Due Date | Risk (L/M/H) | Mitigation | Score (0-2)
H | Chart of accounts harmonised; dimensions/segments defined. | [6 empty] | 1
H | Item master cleansed (UoM, categories, attributes, costing).
H | Customer & supplier master data cleansed (duplicates removed).
M | Historic data migration strategy agreed (what, how far back).
M | Integration inventory: systems to connect, direction of data, frequency.
L | API/iPaaS approach selected; event/webhook needs identified.
1

## 5_People_Change
Priority (H/M/L) | Requirement / Question | Evidence / Notes | Owner | Status | Due Date | Risk (L/M/H) | Mitigation | Score (0-2)
H | RACI defined for project and BAU roles (sponsor, PM, SMEs, super users). | [6 empty] | 2
H | Training plan (role-based), comms plan, and hypercare defined.
M | Time commitment secured from key SMEs (backfill considered).
M | Change impacts assessed (policy/process updates, controls).
L | Adoption KPIs defined (usage, cycle times, error rates).
2

## 6_Security_Compliance
Priority (H/M/L) | Requirement / Question | Evidence / Notes | Owner | Status | Due Date | Risk (L/M/H) | Mitigation | Score (0-2)
H | Role-based access model drafted (least privilege, SoD). | [6 empty] | 1
H | Audit, logging, and retention needs documented.
M | Data residency, privacy, and industry compliance validated.
M | Backup/DR objectives agreed (RPO/RTO) with vendor/IT.
L | Third-party add-ons reviewed for security posture.
1

## 7_Vendor_Shortlist_Evaluation
Priority (H/M/L) | Requirement / Question | Evidence / Notes | Owner | Status | Due Date | Risk (L/M/H) | Mitigation | Score (0-2)
H | Weighted scorecard created (must-haves vs nice-to-haves).
H | Shortlist of 2–3 vendors aligned to outcomes and industry fit.
M | Reference calls with similar customers completed.
M | TCO modelled (licences, implementation, integrations, support).
L | Contract/commercial guardrails drafted (SLAs, exit, data).
0

## 8_Pilot_Rollout_Plan
Priority (H/M/L) | Requirement / Question | Evidence / Notes | Owner | Status | Due Date | Risk (L/M/H) | Mitigation | Score (0-2)
H | Pilot defined with real data for a critical process (e.g., quote-to-cash).
H | Phase 1 scope, timeline, and resourcing agreed.
M | Cutover plan drafted (freeze windows, reconciliations, POD).
M | Reporting & dashboard requirements validated.
L | Post-go-live success metrics and review cadence set.
0

## 9_Budget_TCO
Priority (H/M/L) | Requirement / Question | Evidence / Notes | Owner | Status | Due Date | Risk (L/M/H) | Mitigation | Score (0-2)
H | Budget approved for Phase 1 (licences + implementation + change).
M | Multi-year TCO and benefit case documented.
L | Contingency set for data, integrations, and change management.
0